## Product Backlolg
The Solution Stack - Oil and Gas Royalty Calculation System
Backlog Item | Priority | Status | 2016-01-19 | 2016-01-26 | 2016-02-02 | 2016-02-09 | 2016-02-16
Get the code working as is: GUI, Calculation, Worksheet
Demo and obtain feedback
Refreash
Establish and Document all practices and tools (Case Study) (Very simple, maybe just a descriptioin and a url. (Adrienne write a blog?) - Scrum, Python, GIT, TDD, Flask, sqlite, sql…
Create new project???
Create TDD Strategy (Coverage, No Code without a test)
Create Data Access Strategy
Create Data Utilities (Copy from excel to sqlite, sqlite to excel, test strategy)
Create a reporting strategy
Start implementing component by component
Calculations
Sask Oil
GOOR
IOGR 1995: http://laws-lois.justice.gc.ca/eng/regulations/SOR-94-753/index.html
Sask Gas
Alta Oil
Alta Gas
Work Sheets
Sask Oil
GOOR
IOGR 1995: http://laws-lois.justice.gc.ca/eng/regulations/SOR-94-753/index.html
Sask Gas
Alta Oil
Alta Gas
CRUD
Royalty Master
Well
Reports
By Payer
By Area
By Lease
By …

## Ceremonies
1 | Sprint Planning
2 | Daily Stand-up
3 | Sprint demo
4 | Sprint retrospective