## Product Backlolg
The Solution Stack - Oil and Gas Royalty Calculation System
Backlog Item | Priority | Status | 2016-01-19 | 2016-01-26 | 2016-02-02 | 2016-02-09 | 2016-02-16
Get the code working as is: GUI, Calculation, Worksheet
Add worksheet to GUI
Demo and obtain feedback
Validate Worksheet and Calc for SaskCrown Oil
Adrienne Learn python test
Get System running on Adrienne's machine
Refreash
Establish and Document all practices and tools (Case Study) (Very simple, maybe just a descriptioin and a url. (Adrienne write a blog?) Best Practices - Scrum, Python, GIT, TDD, Flask, sqlite, sql…
Create TDD Strategy (Coverage, No Code without a test)
Create Data Access Strategy
Create Data Utilities (Copy from excel to sqlite, sqlite to excel, test strategy)
Create a reporting strategy
Start implementing component by component
Help System
Create new project???
Calculations
Sask Oil
GOOR
IOGR 1995: http://laws-lois.justice.gc.ca/eng/regulations/SOR-94-753/index.html
Sask Gas
Alta Oil
Alta Gas
Work Sheets
Sask Oil
GOOR
IOGR 1995: http://laws-lois.justice.gc.ca/eng/regulations/SOR-94-753/index.html
Sask Gas
Alta Oil
Alta Gas
CRUD
Royalty Master
Well
Reports
By Payer
By Area
By Lease
By …

## Ceremonies
1 | Sprint Planning
2 | Daily Stand-up
3 | Sprint demo
4 | Sprint retrospective

## Sprint1
|  |  | Est | Wed
Hours
Complete tests for Sask CrownRoyalty Rate | A |  | 5
Brake out Used Royalty Rate | A |  | 5
Refactor DB Load with test | K |  | 14
Write the our version of orm | K |  | 14
Read organization of tests | K |  | 1
Complete tests IORG1995 | A |  | 10
Finish IOGR1995 | A |  | 5
Validate Worksheet and Calc for SaskCrown Oil | L |  | 2
Setup new project and new dirctory structure | K
Create a model module with tests and convensions (Where do our test go, nameing convension) | K
Implement Missing IOGR1995 Supplementary Royalty with tests | A
Write Tests and restructure calcSaskOilProvCrown | A
Write DB Load utilities for testing
Adrienne - Test Drivin Development, Python code
Konstantin - sqlite, calcs
Larry - Utilities help
Get the code working as is: GUI, Calculation, Worksheet | K | Done | 1
Add worksheet to GUI | K | Cancel | 3
Demo and obtain feedback | L | Done | 14
Adrienne Learn python test | A | Done | 7
Get System running on Adrienne's machine | K | Done | 3
Get TDD running in Adrienne's machine | K&A
Review and Learn Existing Calcs | A | Done
Create TDD Strategy (Coverage, No Code without a test) | K | Done | 10
Create Data Access Strategy Step 1 example | L | Dane | 10